## Overview
NOTE: do not edit this sheet (beyond duplicating the last row as outlined in the User Guide) - all its data is collected from the named sheets (column A)
Game Company
Asset | [6 empty] | Next Milestone |  |  |  | QA |  |  | Alpha Version (Date) | Beta Version | PLAYGEN | GAMEWARE | NUROGAMES | BIP
Asset Id | Descriptive name | Partner | Code | Design | Demo | Used | Name | % done | Days left | Delayed Tasks | Musts | Shoulds | Progress
2.1a | Client Tracker | UCM | OK | OK | OK | OK | m3: add QA documentation | 30 | #VALUE! | 0 | 6 | 2 | 46.15%
2.1b | SS Interaction Storage and Analytics | UCM | OK | OK | OK | OK | #N/A | #N/A | #N/A | 0 | 7 | 6 | 53.85%
2.2a | Step based competence assessment | UU | OK | OK | OK | OK | m2: 2nd release | 0.0 | 113 | 0 | 12 | 9 | 92.31%
2.2b | T2.2C - Domain Model | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
2.2c | T2.2B - ANOTHER client-side non-intrusive competence assesment ! | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
2.2d | Cognitive Capacity Measurement [ON HOLD] | OUNL | NO | NO | NO | NO | m2: (dummy milestone 2) | 0 | 7 | 0 | 0 | 0 | 0%
2.2e | Performance Statistics | OUNL | NO | OK | NO | OK | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
2.3a | Real-time Emotion Detection | OUNL | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
2.3b | ReaderBench - Sentiment Analysis on Texts | UPB | OK | OK | OK | NO | #N/A | #N/A | #N/A | 0 | 1 | 2 | 7.692%
2.3c | T2.3C - Motivation Assessment | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
2.3d | Real-Time Arousal Detection Using Galvanic Skin Response | TUSofia | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
2.4a | Authentication & Authorization | UCM | OK | OK | OK | OK | m8: add QA documentation | 0 | #VALUE! | 0 | 8 | 6 | 66.67%
2.4b | Server-side Dashboard and Analysis | UCM | OK | OK | OK | OK | #N/A | #N/A | #N/A | 0 | 7 | 6 | 53.85%
2.4c | Game Storage | OUNL | OK | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.1a | Emotional Appraisal | INESC-ID / GAIPS | OK | OK | OK | OK | #N/A | #N/A | #N/A | 0 | 1 | 0 | 8.333%
3.1b | Emotion Decision Making | INESC-ID / GAIPS | OK | OK | OK | OK | #N/A | #N/A | #N/A | 0 | 1 | 0 | 8.333%
3.1c | IDeA - Identity Driven Agents | INESC-ID / GAIPS | NO | NO | NO | NO |  |  | #N/A | 0 | 0 | 0 | 0%
3.1d | ToMAss [ON HOLD] | OUNL | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.1e | Social Importance Dynamics (SID) Model | INESC-ID / GAIPS | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.2a | Virtual Human Controller | UU | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.2b | Motion Builder | UU | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.3a | ReaderBench - Semantic Models and Topic Mining | UPB | OK | OK | OK | NO | #N/A | #N/A | #N/A | 0 | 1 | 2 | 7.692%
3.3b | ReaderBench - Automated Essay Grading | UPB | OK | OK | OK | NO | #N/A | #N/A | #N/A | 0 | 1 | 2 | 7.692%
3.3c | ReaderBench - Automated Assessment of Participation and Collaboration in CSCL Conversations | UPB | OK | OK | OK | NO | #N/A | #N/A | #N/A | 0 | 1 | 2 | 7.692%
3.3d | ReaderBench - Automated Identification of Reading Strategies | UPB | OK | OK | OK | NO | #N/A | #N/A | #N/A | 0 | 1 | 2 | 7.692%
3.3e | Communication Scenario Editor | UU | OK | OK | OK | OK | m2: 2nd release | 0.0 | 113 | 0 | 13 | 11 | 100%
3.3f | Speech I/O | INESC-ID / L2F | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.4a | Heterogeneous Adaptation (HAT) | OUNL | OK | OK | OK | OK | m5: Having an option to update only player ratings. | 0 | 53 | 0 | 4 | 2 | 30.77%
3.4b | Cognitive Load Personalisation [ON HOLD] | OUNL | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.4c | T3.4C - Competence-based Personalisation and Recommendation | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
3.4d | T3.4D - Motivational Adaptation | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
3.4e | T3.4E - Game Configuration | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
3.4f | T3.4F - Cognitive Intervention | TUGraz | OK | OK | NO | NO | #N/A | #N/A | #N/A | 0 | 1 | 0 | 7.692%
3.4g | Player-centric rule-and-pattern-based adaptation | TUSofia | NO | NO | OK | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.5a | Role-play Virtual Character | INESC-ID / GAIPS | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.5b | Authorial Agents | INESC-ID / GAIPS | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
3.6a | Social Gamification Components | PlayGen | OK | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 4 | 2 | 30.77%
3.7a | Integrated Authoring Tool | INESC-ID | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
Template | 0 | U?? | NO | NO | NO | NO | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0%
NOTE: do not edit this sheet (beyond duplicating the last row as outlined in the User Guide) - all its data is collected from the named sheets (column A)
Asset is on hold; sheet currently hidden
Formulas:
Next Milestone = INDEX(INDIRECT("'" & [Asset] & "'!A12:D48"), MATCH(TODAY(), INDIRECT("'" & [Asset] & "'!A12:A48"), -1), 3) & ": " & INDEX(INDIRECT("'" & [Asset] & "'!A12:D48"), MATCH(TODAY(), INDIRECT("'" & [Asset] & "'!A12:A48"), -1), 2)
Days left = INDEX(INDIRECT("'" & [Asset] & "'!A12:G48"), MATCH(TODAY(), INDIRECT("'" & [Asset] & "'!A12:A48"), -1), 7)

## 2.1a
Asset id | Client Tracker | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UCM | [6 empty] | must | License | Apache 2.0 (http://www.apache.org/licenses/) | (url to RAGE-approved license)
Contact | manuel.freire@fdi.ucm.es | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/206 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/e-ucm/unity-tracker | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1_XtAMvI9mNhR5Qxc9RHF6OWhRBJyL2Iq6biAwtZegAQ/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | https://github.com/e-ucm/QuizDemo | for evaluation use by game developers | [5 empty] | must | API doc for API users | n.a. | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 5 | All use-cases | [5 empty] | must | Build & run instructions | https://github.com/e-ucm/unity-tracker/blob/master/README.md | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable | n.a. | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-15 | add QA documentation | m3 | 30 | 0.5 | #VALUE! | #VALUE! |  | must | Project overview page |  | (url to project overview page)
2016-02-29 | merge with WvdW's code | m2 | 26.9231 | 1.3 | #VALUE! | #VALUE! | pending coordination with Wim | must | Deployment instructions | https://github.com/e-ucm/rage-analytics/wiki/Tracker | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2015-10-10 | release demo | m1 | 100 | 1.2 | #VALUE! | done |  | must | Tutorial / quickstart | https://github.com/e-ucm/unity-tracker/blob/master/README.md | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code | https://github.com/e-ucm/QuizDemo | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation | https://github.com/e-ucm/QuizDemo/blob/master/README.md | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
Tasks
design doc ref | description | milestone ref | % complete | total work (mm) | est. date (if delayed) | work complete (mm) | Notes (mandatory to describe delays)
t1.1 | get WvdW's build environment automated | m2 | 50 | 0.3 |  | 0.15
t1.2 | merge with WvdW's code | m2 | 20 | 1 |  | 0.2
t2.1 | write detailed doc | m3 | 30 | 0.5 |  | 0.15
t3.1 | release demo | m1 | 100 | 1.2 |  | 1.2
Formulas:
est. days left = IF(D12 = 100, "done", [estimated finish date] - TODAY())

## 2.1b
Asset id | SS Interaction Storage and Analytics | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UCM | [6 empty] | must | License | Apache 2.0 (http://www.apache.org/licenses/) | (url to RAGE-approved license)
Contact | manuel.freire@fdi.ucm.es | [6 empty] | should | Coding guidelines | https://github.com/e-ucm/rage-analytics-backend/blob/master/.jscsrc | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/220 | [6 empty] | should | Unit tests | npm test | (command or UI action to run tests)
Code repo | https://github.com/e-ucm/rage-analytics-backend | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1imtLyI59yOv9CrPRZdSu8UaUmGs_3ZyxhQYphcmnUPE/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools | https://codeclimate.com/github/e-ucm/rage-analytics-backend | (commands or UI actions used to run analyses)
Demo | https://github.com/e-ucm/rage-analytics-backend/releases/latest | for evaluation use by game developers | [5 empty] | must | API doc for API users | http://e-ucm.github.io/rage-analytics-backend/ | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 5 | explain who is using it | [5 empty] | must | Build & run instructions | https://github.com/e-ucm/rage-analytics | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable | n.a. | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration | https://travis-ci.org/e-ucm/rage-analytics-backend | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests | npm test | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script | https://github.com/e-ucm/rage-analytics | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. | https://github.com/e-ucm/a2/wiki/Deployment | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. | https://david-dm.org/e-ucm/rage-analytics-backend | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide | https://github.com/e-ucm/a2/wiki/Contributing | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.2a
Asset id | Step based competence assessment | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UU | [6 empty] | must | License | https://github.com/UURAGE/ScenarioReasoner/blob/master/LICENSE.txt | (url to RAGE-approved license)
Contact | r.lala@uu.nl; j.t.jeuring@uu.nl | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/269 | [6 empty] | should | Unit tests | We plan to use QuickCheck | (command or UI action to run tests)
Code repo | https://github.com/UURAGE/ScenarioReasoner | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://github.com/UURAGE/ScenarioReasoner/blob/master/doc/SDD%20Scenario%20Reasoner%20v3.pdf | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools | The Haskell language/compiler has built-in strong static checking; and we also use the Haskell type-checker. | (commands or UI actions used to run analyses)
Demo | https://github.com/UURAGE/ScenarioReasoner | for evaluation use by game developers | [5 empty] | must | API doc for API users | n.a. | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 2 | Nurogames, BIP Media, Playgen(?) | [5 empty] | must | Build & run instructions | https://github.com/UURAGE/ScenarioReasoner/blob/master/ScenarioReasoner.cabal | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable | n.a | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. | n.a. | (url to rage metadata document within repository)
2016-06-30 | 2nd release | m2 | 0.0 | 4 | 2016-06-30 | 113 |  | must | Project overview page | https://communicate.sites.uu.nl | (url to project overview page)
2016-02-29 | Evaluation release | m1 | 90 | 5 | 2016-02-29 | -9 |  | must | Deployment instructions | https://github.com/UURAGE/ScenarioReasoner/blob/master/ScenarioReasoner.cabal | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart | https://www.youtube.com/watch?v=tOc0P0tT1yE | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide | n.a. | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration | n.a. | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests | See Tech report | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results | http://www.cs.uu.nl/research/techreps/repo/CS-2014/2014-005.pdf | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script | https://github.com/UURAGE/ScenarioReasoner/blob/master/README.md | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. | https://github.com/UURAGE/ScenarioReasoner/blob/master/README.md | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. | https://github.com/UURAGE/ScenarioReasoner/blob/master/README.md | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. | See SDD | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide | n.a. | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors | n.a. | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 90 | 5 |  | 4.5
t1.2 | sample task 1.2 | m2 | 0 | 4 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.2b
Asset id | T2.2C - Domain Model | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Domain%20Model%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo |  | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.2c
Asset id | T2.2B - ANOTHER client-side non-intrusive competence assesment ! | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Non-intrusive%20Competence%20Assessment%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.2d
Asset id | Cognitive Capacity Measurement [ON HOLD] | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | Giel.vanLankveld@ou.nl | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/242 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-15 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-15 | 6 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.2e
Asset id | Performance Statistics | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | Giel.vanLankveld@ou.nl | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/243 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://rage.ou.nl/filedepot/folder/17 | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 2 | Used by (5.2 and 5.3) | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-01 | Collection and storage of data | m1 | 100 | 1 | 2016-03-01 | done | Done through assets 2.1A and 2.1B | must | Project overview page |  | (url to project overview page)
2016-04-01 | Java server-side components for selection and analysis of data | m2 | 10 | 1 | 2016-04-01 | 23 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-05-01 | Javascript server-side visualisation of statistics | m3 | 0.0 | 1 | 2016-05-01 | 53 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Functionality of available communication assets | m1 | 100 | 1 |  | 1
t1.2 | Functionality of available data storage assets | m2 | 100 | 1 |  | 1
t2.1 | Query for data selection | m3 | 0 | 1 |  | 0
t2.2 | Validation of data selection | m4 | 0 | 1 |  | 0
t2.3 | Interface for teacher for analysis selection | m5 | 0 | 1 |  | 0
t3.1 | Implementation of statistical analyses | m6 | 0 | 1 |  | 0
t3.2 | Validation and testing of correct analysis results | m7 | 0 | 1 |  | 0
t4.1 | Web interface for teacher for selection of visualization | m8 | 0 | 1 |  | 0
t4.2 | Data visualization in table form | m9 | 0 | 1 |  | 0
t4.3 | Data visualization in graph form | m10 | 0 | 1 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.3a
Asset id | Real-time Emotion Detection | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | kiavash.bahreini@ou.nl | [5 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | https://rage.ou.nl/node/223 | [5 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | https://rage.ou.nl/filedepot/folder/18 | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.3b
Asset id | ReaderBench - Sentiment Analysis on Texts | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UPB | [6 empty] | must | License | https://bitbucket.org/ReaderBench/readerbench/src/b0dcd2ad9c9db42e3a7d779d40bfb0d0b8ba21e1/LICENSE.txt?fileviewer=file-view-default | (url to RAGE-approved license)
Contact | mihai.dascalu@cs.pub.ro | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/285 | [6 empty] | should | Unit tests | To be published | (command or UI action to run tests)
Code repo | https://bitbucket.org/ReaderBench/readerbench | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://bitbucket.org/ReaderBench/readerbench | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | http://readerbench.com/demo/text-processing | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Preliminary release | m1 | 50.0 | 0.3 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sentiment valences integration | m1 | 50 | 0.3 |  | 0.15
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.3c
Asset id | T2.3C - Motivation Assessment | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Motivation%20Assessment%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.3d
Asset id | Real-Time Arousal Detection Using Galvanic Skin Response | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUSofia | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | ddessy@gmail.com | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/321 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/ddessy/RealTimeArousalDetectionUsingGSR | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://github.com/ddessy/RealTimeArousalDetectionUsingGSR/Docs | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | Not yet available | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-01-30 | Design (asset & device) | m1 | 100 | 0.5 | 2016-01-30 | done |  | must | Project overview page |  | (url to project overview page)
2016-03-29 | Implementation (asset & device) | m2 | 37.5 | 2.4 | 2016-03-29 | 20 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-04-18 | Testing (asset & device) | m3 | 18.4615 | 1.3 | 2016-04-18 | 40 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
2016-04-25 | Documentation | m4 | 0 | 0.3 | 2016-04-25 | 47 |  | must | Executable demo |  | (url to executable demo)
2016-05-10 | Demo | m5 | 0 | 0.5 | 2016-05-10 | 62 |  | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | 1. Asset architecture and API design | m1 | 100 | 0.5 |  | 0.5
t2 | 2. GSR Device design | m2 | 100 | 0.3 |  | 0.3
t3 | 3. GSR Device functionality tests | m3 | 80 | 0.3 |  | 0.24
t4 | 4. GSR signal read and visualization | m2 | 100 | 0.6 |  | 0.6
t5 | 5. GSR features and arousal metrics calculation | m2 | 0 | 1.5 |  | 0
t6 | 6. Asset testing (coverage/unit/integration/performance tests) | m3 | 0 | 1 |  | 0
t7 | 7. Asset documentation (API doc, deployment instruction, tutorial, demo documentation) | m4 | 0 | 0.3 |  | 0
t8 | 8. Asset demo | m5 | 0 | 0.5 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.4a
Asset id | Authentication & Authorization | [6 empty] | QA: Codebase
Partner | UCM | [6 empty] | License | Apache 2.0 (http://www.apache.org/licenses/) | (url to RAGE-approved license)
Contact | manuel.freire@fdi.ucm.es | [6 empty] | Coding guidelines | https://github.com/e-ucm/a2/blob/master/.jscsrc | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/326 | [6 empty] | should | Unit tests | npm test | (command or UI action to run tests)
Code repo | https://github.com/e-ucm/a2 | repository must include build instructions | [5 empty] | should | Coverage | (72%; Coveralls https://coveralls.io/github/e-ucm/a2) | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1Ve6qGs30uGUYrlMBsB-UrIMaaFw2VdbSKROml8_TT78/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools | https://codeclimate.com/github/e-ucm/a2 | (commands or UI actions used to run analyses)
Demo | https://github.com/e-ucm/rage-auth2 | for evaluation use by game developers | [5 empty] | must | API doc for API users | http://e-ucm.github.io/a2/ | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 5 | Indirectly, all use-cases; directly, all UCM assets - and some non-UCM server-side assets | [5 empty] | must | Build & run instructions | npm install && npm run fast-setup && npm start | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-15 | add QA documentation | m8 | 0 | 0 | #VALUE! | #VALUE! |  | must | Project overview page |  | (url to project overview page)
2016-02-29 | add OAuth2 support | m7 | 0 | 0 | #VALUE! | #VALUE! | https://github.com/e-ucm/a2/tree/1.0.0 | must | Deployment instructions | https://github.com/e-ucm/a2/wiki/Deployment | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2015-11-10 | release demo | m1 | 100 | 3.2 | #VALUE! | done | https://github.com/e-ucm/a2/commit/a5fb36fbae36de850f74da89b5bb69b587ea2153 | must | Tutorial / quickstart | https://github.com/e-ucm/a2/wiki | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo | https://hub.docker.com/r/eucm/a2/ | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration | https://travis-ci.org/e-ucm/a2 | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests | npm test | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script | https://github.com/e-ucm/rage-analytics | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. | https://github.com/e-ucm/a2/wiki/Deployment | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. | https://david-dm.org/e-ucm/a2 | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide | https://github.com/e-ucm/a2/wiki/Contributing | (url to docs describing guidelines for those wishing to contribute code)
[7 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
(unhide rows to expand the formula)
Tasks
design doc ref | description | milestone ref | % complete | total work (mm) | est. date (if delayed) | work complete (mm) | Notes (mandatory to describe delays)
1.1 | Allow users to log in and out | m1 | 100 | 0.5 |  | 0.5
1.2 | Manage users | m1 | 100 | 0.3 |  | 0.3
1.3 | Manage user roles | m1 | 100 | 0.6 |  | 0.6
2.1 | Manage Applications | m1 | 100 | 1 |  | 1
3.1 | Proxy client requests to applications after checking authentications & authorization | m1 | 100 | 0.8 |  | 0.8
|  | m2 | 100 | 0.5 |  | 0.5
|  | m2 | 100 | 0.5 |  | 0.5
Formulas:
est. days left = IF(D12 = 100, "done", [estimated finish date] - TODAY())

## 2.4b
Asset id | Server-side Dashboard and Analysis | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UCM | [6 empty] | must | License | Apache 2.0 (http://www.apache.org/licenses/) | (url to RAGE-approved license)
Contact | manuel.freire@fdi.ucm.es | [6 empty] | should | Coding guidelines | https://github.com/e-ucm/rage-analytics-frontend/blob/master/.jscsrc | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/225 | [6 empty] | should | Unit tests | npm test | (command or UI action to run tests)
Code repo | https://github.com/e-ucm/rage-analytics-frontend | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/13rrTugiezXwNTfXriQeg1l-jb0H4Jil7l4inpXCVvm8/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools | https://codeclimate.com/github/e-ucm/rage-analytics-frontend | (commands or UI actions used to run analyses)
Demo | https://github.com/e-ucm/rage-analytics-frontend/releases/latest | for evaluation use by game developers | [5 empty] | must | API doc for API users | n.a. | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 5 | All games | [5 empty] | must | Build & run instructions | https://github.com/e-ucm/rage-analytics | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable | n.a. | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration | https://travis-ci.org/e-ucm/rage-analytics-frontend | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests | npm test | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script | https://github.com/e-ucm/rage-analytics | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. | https://github.com/e-ucm/a2/wiki/Deployment | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. | https://david-dm.org/e-ucm/rage-analytics-frontend | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide | https://github.com/e-ucm/a2/wiki/Contributing | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 2.4c
Asset id | Game Storage | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | wim.vandervegt@ou.nl | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/312 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/rageappliedgame/ClientSideGameStorageAsset | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-05 | Storing and restoring structure. | m2 | 0 | 3 | 2016-03-05 | -4 |  | must | Project overview page |  | (url to project overview page)
2016-03-05 | Integration with storage (IDataStorage, IVirtualProperties). | m3 | 0 | 0 | 2016-03-05 | -4 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-05 | Integration with storage (IWebServiceRequest). | m4 | 0 | 0 | 2016-03-05 | -4 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
2016-03-01 | Serialization using XML. | m1 | 0 | 0.3 | 2016-03-01 | -8 |  | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F53:F56, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.1a
Asset id | Emotional Appraisal | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License | https://github.com/GAIPS-INESC-ID/FAtiMA-Emotional-Appraisal/blob/master/License.txt | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/209 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/GAIPS-INESC-ID/FAtiMA-Emotional-Appraisal | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1JMr-WD8KKNUgCyFrK8oRiScKwd_Ywf7txvBsOwirDs0/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | https://bitbucket.org/UrusaiDaisei/rage-demos | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 1 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-16 | Finish the authoring tool | m2 | 80.0 | 0.3 | 3/16/2016 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
must
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Add the ability to create events in the authoring tool | m2 | 80 | 0.3 |  | 0.24
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.1b
Asset id | Emotion Decision Making | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License | https://github.com/GAIPS-INESC-ID/FAtiMA-Emotional-Appraisal/blob/master/License.txt | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/210 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/GAIPS-INESC-ID/FAtiMA-Emotional-Appraisal | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1_fLg5TYfdZfjY6oiy56JZFClGaw_YcqYER87NAjR0sM/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | https://bitbucket.org/UrusaiDaisei/rage-demos | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 1 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | Finish the authoring tool | m1 | 20.0 | 0.3 | 3/30/2016 | 21 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
must
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Finish the authoring tool | m1 | 20 | 0.3 |  | 0.06
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.1c
Asset id | IDeA - Identity Driven Agents | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.1d
Asset id | ToMAss [ON HOLD] | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.1e
Asset id | Social Importance Dynamics (SID) Model | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/212 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/GAIPS-INESC-ID/FAtiMA-Emotional-Appraisal | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://docs.google.com/document/d/1xKQUEXE3igJRBTuOVD88btxDeG09XGKF-VzG7UbKa-s/edit?usp=sharing | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | Finish the first release | m1 | 20.0 | 0.3 | 3/30/2016 | 21 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Implement SI Attribution Rules | m1 | 20 | 0.3 |  | 0.06
t1.2 | Implement SI Claims | m2 | 0 | 3 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.2a
Asset id | Virtual Human Controller | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UU | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.2b
Asset id | Motion Builder | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UU | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3a
Asset id | ReaderBench - Semantic Models and Topic Mining | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UPB | [6 empty] | must | License | https://bitbucket.org/ReaderBench/readerbench/src/b0dcd2ad9c9db42e3a7d779d40bfb0d0b8ba21e1/LICENSE.txt?fileviewer=file-view-default | (url to RAGE-approved license)
Contact | mihai.dascalu@cs.pub.ro | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/244 | [6 empty] | should | Unit tests | To be published | (command or UI action to run tests)
Code repo | https://bitbucket.org/ReaderBench/readerbench | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://bitbucket.org/ReaderBench/readerbench | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | http://readerbench.com/demo/text-processing | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Preliminary release | m1 | 65.0 | 0.3 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | semantic models integration | m1 | 65 | 0.3 |  | 0.195
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3b
Asset id | ReaderBench - Automated Essay Grading | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UPB | [6 empty] | must | License | https://bitbucket.org/ReaderBench/readerbench/src/b0dcd2ad9c9db42e3a7d779d40bfb0d0b8ba21e1/LICENSE.txt?fileviewer=file-view-default | (url to RAGE-approved license)
Contact | mihai.dascalu@cs.pub.ro | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/245 | [6 empty] | should | Unit tests | To be published | (command or UI action to run tests)
Code repo | https://bitbucket.org/ReaderBench/readerbench | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://bitbucket.org/ReaderBench/readerbench | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | http://readerbench.com/demo/semantic-annotation | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Preliminary release | m1 | 60.0 | 0.3 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | automated essay grading integration | m1 | 60 | 0.3 |  | 0.18
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3c
Asset id | ReaderBench - Automated Assessment of Participation and Collaboration in CSCL Conversations | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UPB | [6 empty] | must | License | https://bitbucket.org/ReaderBench/readerbench/src/b0dcd2ad9c9db42e3a7d779d40bfb0d0b8ba21e1/LICENSE.txt?fileviewer=file-view-default | (url to RAGE-approved license)
Contact | mihai.dascalu@cs.pub.ro | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/246 | [6 empty] | should | Unit tests | To be published | (command or UI action to run tests)
Code repo | https://bitbucket.org/ReaderBench/readerbench | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://bitbucket.org/ReaderBench/readerbench | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | http://readerbench.com/demo/cscl | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Preliminary release | m1 | 80.0 | 0.3 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | CSCL processing | m1 | 80 | 0.3 |  | 0.24
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3d
Asset id | ReaderBench - Automated Identification of Reading Strategies | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UPB | [6 empty] | must | License | https://bitbucket.org/ReaderBench/readerbench/src/b0dcd2ad9c9db42e3a7d779d40bfb0d0b8ba21e1/LICENSE.txt?fileviewer=file-view-default | (url to RAGE-approved license)
Contact | mihai.dascalu@cs.pub.ro | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/248 | [6 empty] | should | Unit tests | To be published | (command or UI action to run tests)
Code repo | https://bitbucket.org/ReaderBench/readerbench | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://bitbucket.org/ReaderBench/readerbench | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | http://readerbench.com/demo/self-explanation | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Preliminary release | m1 | 80.0 | 0.3 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
[8 empty] | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Self Explanation | m1 | 80 | 0.3 |  | 0.24
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3e
Asset id | Communication Scenario Editor | [6 empty] | RFC2119 Level | QA: Codebase
Partner | UU | [6 empty] | must | License | https://github.com/UURAGE/ScenarioEditor/blob/master/LICENSE.txt | (url to RAGE-approved license)
Contact | r.lala@uu.nl; j.t.jeuring@uu.nl | [6 empty] | should | Coding guidelines | To be published | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/249 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/UURAGE/ScenarioEditor | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://github.com/UURAGE/ScenarioEditor/blob/master/doc/SDD%20Scenario%20Editor%20v3.pdf | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools | JSHint een static code analysis tool | (commands or UI actions used to run analyses)
Demo | http://www.communicategame.nl/UURAGE/ScenarioEditor/ | for evaluation use by game developers | [5 empty] | must | API doc for API users | n.a | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 5 | Nurogames, Hull, Randstad, BIP, Okkam, Playgen | [5 empty] | must | Build & run instructions | https://github.com/UURAGE/ScenarioEditor/blob/master/README.md | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable | n.a | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. | n.a | (url to rage metadata document within repository)
2016-06-30 | 2nd release | m2 | 0.0 | 4 | 2016-06-30 | 113 |  | must | Project overview page | https://communicate.sites.uu.nl | (url to project overview page)
2016-02-29 | Evaluation release | m1 | 90 | 5 | 2016-02-29 | -9 |  | must | Deployment instructions | https://github.com/UURAGE/ScenarioEditor/blob/master/README.md | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart | https://youtu.be/eaLblvbmPOU | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo | http://www.communicategame.nl/UURAGE/ScenarioEditor/ | (url to executable demo)
[8 empty] | should | Demo source-code | https://github.com/UURAGE/ScenarioEditor | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation | https://github.com/UURAGE/ScenarioEditor | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide | none | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration | n.a | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests | n.a | (commands or UI actions to run tests)
[8 empty] | should | Load tests | Planned for next release | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results | Planned for next release | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script | https://github.com/UURAGE/ScenarioEditor/blob/master/README.md | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. | https://github.com/UURAGE/ScenarioEditor/blob/master/README.md | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. | Browser with WebGL | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. | See SDD | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide | n.a | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors | n.a | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 90 | 5 |  | 4.5
t1.2 | sample task 1.2 | m2 | 0 | 4 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.3f
Asset id | Speech I/O | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / L2F | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4a
Asset id | Heterogeneous Adaptation (HAT) | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | Enkhbold.Nyamsuren@ou.nl | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/216 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | https://github.com/rageappliedgame/HatAsset , https://github.com/rageappliedgame/HATWidget | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | https://rage.ou.nl/filedepot/folder/176 | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | https://github.com/E-Nyamsuren/rage-wp3-t3.4-hat | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 1 | HCG (T5.4) | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-12-01 | Preliminary design and prototype of the server-side version | m8 | 0 | 1 | 2016-12-01 | 267 |  | must | Project overview page |  | (url to project overview page)
2016-09-01 | Calculating ratings on the player group level | m9 | 0 | 1 | 2016-09-01 | 176 |  | must | Deployment instructions | https://rage.ou.nl/filedepot?fid=501 | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-09-01 | Accepting accuracy values between 0 and 1. | m6 | 0 | 1 | 2016-09-01 | 176 |  | must | Tutorial / quickstart | https://rage.ou.nl/filedepot/folder/176 | (url to docs intended as a first contact with the asset)
2016-05-01 | Having options for calculating rating based on (1) both time duration and accuracy or (2) accuracy only. | m7 | 0 | 1 | 2016-05-01 | 53 |  | must | Executable demo | https://github.com/E-Nyamsuren/rage-wp3-t3.4-hat | (url to executable demo)
2016-05-01 | Having an option to update only player ratings. | m5 | 0 | 1 | 2016-05-01 | 53 |  | should | Demo source-code | https://github.com/E-Nyamsuren/rage-wp3-t3.4-hat | (url to repository source-code used in demo)
2016-03-01 | Visualization and analysis to aid assessment by teachers and students. | m4 | 100 | 1 | 2016-03-01 | done |  | should | Demo documentation | https://github.com/E-Nyamsuren/rage-wp3-t3.4-hat | (url to docs describing how to run the demo, and what to look for)
2016-03-01 | Client-side XML data management. | m3 | 100 | 1 | 2016-03-01 | done |  | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
2016-03-01 | Learning/performance tracking and assessment | m2 | 100 | 1 | 2016-03-01 | done |  |  | QA: Deployment, lifecycle & contrib. support
2016-03-01 | Player skill to game difficulty adaptation. | m1 | 100 | 1 | 2016-03-01 | done |  | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
2016-03-01 | Demo | m10 | 100 | 1 | 2016-03-01 | done |  | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
F1 | Player skill to game difficulty adaptation. | m1 | 100 | 1 |  | 1
F2 | Learning/performance tracking and assessment | m2 | 100 | 1 |  | 1
F3 | Client-side XML data management. | m3 | 100 | 1 |  | 1
F4 | Visualization and analysis to aid assessment by teachers and students. | m4 | 100 | 1 |  | 1
F5 | Having an option to update only player ratings. | m5 | 0 | 1 |  | 0
F6 | Accepting accuracy values between 0 and 1. | m6 | 0 | 1 |  | 0
F7 | Having options for calculating rating based on (1) both time duration and accuracy or (2) accuracy only. | m7 | 0 | 1 |  | 0
F8 | Preliminary design and prototype of the server-side version | m8 | 0 | 1 |  | 0
F9 | Calculating ratings on the player group level | m9 | 0 | 1 |  | 0
F10 | Demo | m10 | 100 | 1 |  | 1
0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4b
Asset id | Cognitive Load Personalisation [ON HOLD] | [6 empty] | RFC2119 Level | QA: Codebase
Partner | OUNL | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | Giel.vanLankveld@ou.nl | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/node/289 | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4c
Asset id | T3.4C - Competence-based Personalisation and Recommendation | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Competence-based%20Personalisation%20and%20Recommendation%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4d
Asset id | T3.4D - Motivational Adaptation | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Motivational%20Adaptation%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4e
Asset id | T3.4E - Game Configuration | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Game%20Configuration%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 40 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 40 | 1000 |  | 400
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4f
Asset id | T3.4F - Cognitive Intervention | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUGraz | [6 empty] | must | License | Apache 2.0 | (url to RAGE-approved license)
Contact | alexander.nussbaumer@tugraz.at, mmaurer@tugraz.at | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | https://rage.ou.nl/wiki/Cognitive%20Intervention%20Asset | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | http://css-kti.tugraz.at/projects/rage/assets/ | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | http://css-kti.tugraz.at/projects/rage/assets/ | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-06-30 | Evaluation release | m3 | 0 | 1000 | 6/30/2016 | 113 |  | must | Project overview page |  | (url to project overview page)
2016-04-30 | Draft release | m2 | 0 | 1000 | 4/30/2016 | 52 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
2016-03-18 | Asset design and API | m1 | 80 | 1000 | 3/18/2016 | 9 |  | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1 | Update specification, API, and design document | m1 | 80 | 1000 |  | 800
t2 | develop functionality | m2 | 0 | 1000 |  | 0
t3 | test and update functionality | m3 | 0 | 1000 |  | 0
Formulas:
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.4g
Asset id | Player-centric rule-and-pattern-based adaptation | [6 empty] | RFC2119 Level | QA: Codebase
Partner | TUSofia | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | ddessy@gmail.com | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | https://www.youtube.com/watch?v=c46blt9yj9c | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.5a
Asset id | Role-play Virtual Character | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.5b
Asset id | Authorial Agents | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID / GAIPS | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.6a
Asset id | Social Gamification Components | [6 empty] | RFC2119 Level | QA: Codebase
Partner | PlayGen | [6 empty] | must | License | Apache 2.0 (http://www.apache.org/licenses/) | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines | https://github.com/playgenhub/rage-sga-server/blob/master/CodeMaid.config | https://github.com/playgenhub/rage-sga-server/blob/master/SocialGamificationAsset.sln.DotSettings
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests | dnx test | (command or UI action to run tests)
Code repo | https://github.com/playgenhub/rage-sga-serve | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users | http://sga.playgen.com/swagger/ui/index.html | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions | https://github.com/playgenhub/rage-sga-server#installation | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | Alpha version of SGA | m1 | 25.4545 | 3.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | Admin panel fully implemented | m2 | 0 | 0 | 2016-03-16 | 7 |  | must | Deployment instructions | https://github.com/playgenhub/rage-sga-server#installation | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | Matches implementation | m1 | 80 | 0.3 |  | 0.24
t1.2 | Goals implementation | m1 | 20 | 3 |  | 0.6
t1.3 | Implement Goals and Action in admin | m2 | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## 3.7a
Asset id | Integrated Authoring Tool | [6 empty] | RFC2119 Level | QA: Codebase
Partner | INESC-ID | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | samuel.mascarenhas@gaips.inesc-id.pt | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())

## Template
Asset id | [7 empty] | RFC2119 Level | QA: Codebase
Partner | U?? | [6 empty] | must | License |  | (url to RAGE-approved license)
Contact | (your e-mail here) | [6 empty] | should | Coding guidelines |  | (url to guidelines, or to automatted formatting config. file)
Cat. page | (your RAGE Catalogue url here) | [6 empty] | should | Unit tests |  | (command or UI action to run tests)
Code repo | (your repo URL here) | repository must include build instructions | [5 empty] | should | Coverage |  | (% coverage, and command or UI action used to recalculate)
Design doc | (design doc URL - eg.: in your repo!) | describes what this does; referenced by tasks | [5 empty] | should | Static analysis tools |  | (commands or UI actions used to run analyses)
Demo | (demo URL here) | for evaluation use by game developers | [5 empty] | must | API doc for API users |  | (only if you offer such an API; url to docs; and if automatically generated, commant or UI action to re-generate)
No. of users | 0 | explain who is using it | [5 empty] | must | Build & run instructions |  | (url to instructions describing how to build and test)
[8 empty] | must | Dataset used, if applicable |  | (only if dataset is required to build & test: url to dataset used)
Milestones (by decreasing date) | [8 empty] | QA: End-user experience & doc
date due | description | milestone ref | % complete | total work (pms) | estimated finish date | est. days left | Notes (mandatory to describe delays) | must | RAGE Metadata doc. |  | (url to rage metadata document within repository)
2016-03-30 | (dummy milestone 1) | m1 | 0 | 0.3 | 2016-03-30 | 21 |  | must | Project overview page |  | (url to project overview page)
2016-03-16 | (dummy milestone 2) | m2 | 0 | 3 | 2016-03-16 | 7 |  | must | Deployment instructions |  | (command or UI action to download & deploy asset in minimal, ideally 1, steps)
[8 empty] | must | Tutorial / quickstart |  | (url to docs intended as a first contact with the asset)
[8 empty] | must | Executable demo |  | (url to executable demo)
[8 empty] | should | Demo source-code |  | (url to repository source-code used in demo)
[8 empty] | should | Demo documentation |  | (url to docs describing how to run the demo, and what to look for)
[8 empty] | should | Troubleshooting guide |  | (url to docs with procedures for diagnosing and reporting errors)
QA: Deployment, lifecycle & contrib. support
[8 empty] | should | Cont. Integration |  | (name or, if available online, url to CI integration system used)
[8 empty] | should | Integration tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load tests |  | (commands or UI actions to run tests)
[8 empty] | should | Load test doc. & results |  | (url to docs on how to run; and latest results)
[8 empty] | must | Deployment script |  | (command or URL to create a packaged RAGE asset)
[8 empty] | must | Deployment doc. |  | (url to docs decribing how to run and configure packaged asset)
[8 empty] | must | Platform requirements doc. |  | (url to docs with software and hardware platform requirements)
[8 empty] | must | Dependencies doc. |  | (url to docs describing library dependencies; or configuration file used for automated dependency management)
[8 empty] | should | Contributor guide |  | (url to docs describing guidelines for those wishing to contribute code)
[8 empty] | should | API doc for contributors |  | (command or UI actions to generate developer API doc, such as JavaDoc or Doxygen)
[7 empty] | must | Project overview page |  | (url to project overview page)
Tasks
design doc ref | description | milestone ref | % complete | total work (pms) | est. date (if delayed) | work complete (pms) | Notes (mandatory to describe delays)
t1.1 | sample task 1.1 | m1 | 0 | 0.3 |  | 0
t1.2 | sample task 1.2 | m2 | 0 | 3 |  | 0
Formulas:
estimated finish date = MAX(F52:F55, [Asset id])
est. days left = IF(D12 = 100, "done", [Asset id] - TODAY())